# REQUEST FOR PROPOSAL (RFP)

## Enterprise Cloud Migration Services

Issued by: Global Tech Solutions Inc. Date: January 15, 2024 Proposal Due Date: February 15, 2024 Decision Date: March 1, 2024

## 1. EXECUTIVE SUMMARY

Global Tech Solutions Inc. is seeking a qualified vendor to support the migration and modernization of our enterprise IT infrastructure to cloud-based solutions. We currently operate on-premise data centers with legacy applications and require a comprehensive cloud transformation strategy.

The scope includes infrastructure assessment, cloud platform selection, migration planning, and execution support with minimal business disruption.

## 2. BUSINESS BACKGROUND

Organization: Global Tech Solutions Inc. Industry: Financial Services & Technology Current State: - 500+ employees across 3 locations - Legacy on-premise infrastructure (15+ years old) - 50+ applications (mix of custom and commercial) - 10TB+ of data requiring migration - Annual IT budget: $2.5M

Business Drivers: - Reduce capital expenditure on infrastructure - Improve system reliability and uptime (current SLA: 99.2%, target: 99.95%) - Enable faster deployment of new applications - Improve disaster recovery capabilities - Modernize technology stack

## 3. SCOPE OF WORK

The vendor shall provide the following services:

### Phase 1: Assessment & Planning (Months 1-2)

- Current infrastructure audit

- Application portfolio analysis

- Cloud readiness assessment

- Risk assessment

- Migration roadmap development

### Phase 2: Infrastructure Design (Month 2-3)

- Cloud architecture design (multi-cloud or single cloud)

- Security and compliance design

- Network design and connectivity

- Disaster recovery strategy

### Phase 3: Migration Execution (Months 4-8)

- Infrastructure provisioning in cloud

- Application migration (prioritized waves)

- Data migration and validation

- Testing and UAT support

- Cutover and go-live management

### Phase 4: Optimization & Support (Months 9-12)

- Performance optimization

- Cost optimization

- Knowledge transfer and training

- 90-day post-implementation support

## 4. MANDATORY REQUIREMENTS

Vendors must meet ALL of the following to be considered:

- ISO 27001 Certification - Information Security Management

- Cloud Platform Experience - Minimum 5 years with AWS, Azure, or GCP

- Financial Services Experience - At least 3 completed projects in financial services industry

- Dedicated Account Manager - Full-time primary contact throughout engagement

- 24/7 Support Availability - Support team available 24 hours, 7 days a week

- SLA Guarantee - Minimum 99.9% uptime guarantee

- Performance Bond - Performance bond equal to 10% of contract value

- Team Certifications - At least 10 cloud architects with advanced certifications (AWS Solutions Architect, Azure Solutions Architect, or equivalent)

## 5. EVALUATION CRITERIA

Proposals will be evaluated on the following criteria:

| Criteria | Weight |
| --- | --- |
| Technical Capability & Approach | 40% |
| Cost & Commercial Terms | 30% |
| Experience & References | 20% |
| Team & Staffing | 10% |

### Technical Capability (40%)

- Clarity and feasibility of proposed approach

- Innovation in cloud strategy

- Phased migration plan clarity

- Risk mitigation strategies

- Disaster recovery and business continuity approach

### Cost (30%)

- Overall project cost (fixed vs. time & materials)

- Cost breakdown by phase

- Value for money

- Payment terms

### Experience (20%)

- Number of similar projects completed

- Project success rate

- Reference quality

- Industry-specific experience

### Team (10%)

- Team composition and qualifications

- Relevant experience of key personnel

- Availability and commitment

## 6. BUDGET & PRICING

Estimated Budget Range: $750,000 - $1,500,000

Payment Terms: - 20% upon contract signature - 30% upon completion of Phase 1 - 30% upon completion of Phase 3 - 20% upon completion of Phase 4

Preferred Pricing Model: Fixed price with time & materials for change orders beyond agreed scope

## 7. TIMELINE & MILESTONES

- Week 1-2: Project kickoff and team mobilization

- Month 1: Infrastructure audit complete

- Month 2: Migration roadmap and design complete

- Month 4: Cloud infrastructure live

- Month 8: All applications migrated

- Month 12: Project closure and knowledge transfer complete

## 8. SPECIFIC REQUIREMENTS & CONSTRAINTS

Technical Requirements: - Multi-region deployment capability - Support for both Windows and Linux environments - Database migration support (SQL Server, Oracle, PostgreSQL) - On-premise to cloud hybrid connectivity for transition period - Compliance with financial services regulations (SOC 2 Type II, PCI DSS)

Timeline Constraints: - Cannot migrate during Q2 (business-critical quarter) - Minimal downtime required (maximum 4-hour window per application) - Phased migration approach mandatory

Personnel Constraints: - Vendor must not replace key personnel without approval - Minimum 2 full-time on-site resources for 12 months - Weekly status meetings with executive sponsor

## 9. RISKS & CONCERNS

The following risks have been identified:

- Data Loss Risk - Large data volumes require careful migration planning

- Application Compatibility - Some legacy applications may not be cloud-compatible

- Regulatory Compliance - Financial data handling requires strict compliance

- Business Continuity - Any extended downtime impacts customer services

- Knowledge Gap - Internal IT team limited cloud expertise

## 10. PROPOSAL REQUIREMENTS

Proposing vendors must include:

- Executive Summary (max 2 pages)

- Detailed approach and methodology

- Project timeline and milestone schedule

- Detailed cost breakdown

- Team composition with bios and certifications

- 3-5 references from similar projects

- Risk assessment and mitigation strategies

- Proposed SLAs and performance metrics

- Knowledge transfer and training plan

- Proof of certifications and insurance

Format Requirements: - PDF format - Maximum 50 pages (excluding appendices) - 12-point font minimum - Submitted by February 15, 2024 at 5:00 PM EST

## 11. SELECTION PROCESS

- Mandatory Requirements Review - Vendors not meeting all mandatory requirements will be rejected

- Technical Evaluation - Shortlisted vendors evaluated on technical merits

- Financial Review - Cost analysis of shortlisted proposals

- Reference Checks - Top 3 vendors’ references contacted

- Presentations - Top 2 vendors present to selection committee

- Final Selection - Winner announced by March 1, 2024

## 12. IMPORTANT DATES

| Milestone | Date |
| --- | --- |
| RFP Release | January 15, 2024 |
| Vendor Questions Deadline | January 29, 2024 |
| Clarifications Issued | February 2, 2024 |
| Proposal Due Date | February 15, 2024 |
| Vendor Presentations | February 22-23, 2024 |
| Final Decision | March 1, 2024 |
| Contract Execution | March 8, 2024 |
| Project Kickoff | March 15, 2024 |

## 13. TERMS & CONDITIONS

- Confidentiality: All submissions treated as confidential

- Proprietary Information: Vendor must mark proprietary sections clearly

- Right to Negotiate: Client reserves right to negotiate final terms

- Non-Binding: RFP is non-binding until contract execution

- Question Submissions: All questions submitted via email to procurement@globaltechsolutions.com

Contact: John Smith, Procurement Manager Global Tech Solutions Inc. Email: john.smith@globaltechsolutions.com Phone: (555) 123-4567

END OF RFP